## Slide 1: Re-scope the migration, don't accelerate or pause
Repos are ahead of plan, pipelines are behind
Moving repos without pipelines splits teams across two platforms
Pausing stops progress and measurement
Decision needed: approve the re-scope

## Slide 2: The mechanism works; the metrics are not yet trustworthy
Converted pipeline passes on every pull request
Required check blocks merges that fail
Only 14.9% of builds link to a commit
Lead time is labelled partial until linkage improves

## Slide 3: Move repos only with their pipelines, in three waves
Wave 1: standard products, simple pipelines, pilot teams
Wave 2: complex pipelines, after shared workflows are extended
Wave 3: legacy products, after a runner decision per product
First 90 days: inventory 1,500 pipelines, pilot, name a metric owner

## Slide 4: Enforce in stages, publish only trusted metrics
Audit mode first, then required checks, then enforcement
Stable check names, so a rename does not block every merge
One metric owner; every number shows its coverage
Exceptions have an owner and an expiry date

## Slide 5: Three decisions needed now
CTO: approve the re-scope, name the metric owner, set the end-state date
Security: approve phased enforcement and the legacy runner standard
Product: agree which products move first and how friction is measured